## Project Timeline
Project Name: | Virtual Lab
Project Team Members: | Ajay Strong | Lance Vincent | Parker Owens
Start of class | End of Day
Project Milestone | Due | Details | Notes from Standup with Instructor
Proposal + Team Contract | 2021-03-29 | Propose your idea to two (2) separate instructors for approval
Proof of Concept | 2021-03-31 | Can this idea turn into a reality? What do you need to do to prove it? The point is to identify any technical issues you may have. Determine if your project can be done.
Minimum Viable Product | 2021-04-07 | You have achieved the absolute minimum as far as necessary features show in PoC phase. This may look like you have solved your problem/challenge for at least one case.
Complete Project | 2021-04-12 | Iron out the kinks, receive feedback from peers and instructors, iterate over the MVP
First Draft Script and Demo | 2021-04-14 | Script must be complete and demo'd to instructors/
Recording | 2021-04-16 | Camtasia recording complete
Complete Presentation | 2021-04-17 | Any final touches / editing - Share with friends, family, and social media.
Present Project | 2021-04-24 | Present Projects during graduation/friends & family

## Project Proposal
Project Name:
Project Team Members:
Specifics For Your Project
Overview | - Create a network of VMs to be exploited - Document how an attacker could access sensitive data on the network. - Focus on network attacks to showcase web exploits.
PoC | Currently have three virtual machines with different levels of privilage/access. We wre able to break into the least secured machine using setoolkit via a Credential Harvesting mechanism. The goal is to demonstrate privilage escalation and navigation between machines until web server/database (and thus all sensative information) is accessable.
MVP | Multiple Linux machines have been accessed on the network (minimum of three).
Complete Project | Demonstrating access and escalation in a stepwise fashion. The process will begin at the lowest level machine and culminate in database access breech. The primary attack vector will be web exploits.
Stretch Goals | Access to machines on other operating systems (Windows).

## External Resources
| Link | Notes:
Ex. Github |  | Ex. Repo for our code
Working Doc |  | ex. This is the doc we are sharing / brainstroming on